## Sheet1
S.No | Tasks | Estimated Time | Start | Finish | Predecessors | Resource Name
1 | Feasibilty Study | 4 Days | 2020-01-23 | 2020-01-27
| Team Meeting | 1 Day
| Cost Analysis | 1 Day
| Documentation | 2 Days
| Project Scope | 1 Day |  |  | 1
2 | Design | 15 Days | 2020-01-28 | 2020-02-12
| GUI Designing | 5 Days
| Software Designing | 5 Days
| Database Design | 5 Days |  |  | 2
3 | Code | 45 Days | 2020-02-13 | 2020-03-29
| Develop Code | 28 Days
| Develop GUI | 7 Days
| Integrate | 6 Days
| Initial Testing | 4 Days |  |  | 3
4 | Testing | 21 Days | 2020-03-30 | 2020-04-19
| System Testing | 7 Days
| Exception Handling | 7 Days
| Debugging | 7 Days |  |  | 4